## Slide 1: IBNS 2.0 automation: how the repository works
Run order, job design, rollback and the path to AAP, all through Catalyst Center
Sahban Khan · October 2026
Git
Helios
AAP
DNAC
Notes: This deck is about the repository: what runs first and second, how each job is built, how rollback works, and how it reaches AAP through the existing pipeline. The design decisions (convert in place, golden alongside, three validation layers) are in the earlier deck.

## Slide 2: Eight steps, run in a fixed order around each site
0
Discovery
laptop script
Before anything
Read-only
0b
Classify
classify
Before each site
Read-only
1
Baseline
baseline
1-2 days before, daytime
Read-only
2
Pre-check
precheck
Day of change
Read-only
3
Stage 1
stage1_convert
Change window
Changes config
4
Stage 2
stage2_golden
Same window
Changes config
5
Next-day
nextday_check
Next morning
Read-only
6
Stage 3
stage3_cleanup
After soak
Changes config
Job names above drop the ibns_ prefix. Plus one on-demand job: ibns_rollback_golden re-points ports from the golden config back to the converted config, no reload. Stage 2 also does this automatically on failure.
Notes: Five of the eight steps are read-only and safe to run any time. Only stages 1, 2 and 3 change config, and each saves only after its post-check passes. Discovery runs from my laptop for now because it pulls from Catalyst Center and groups configs; it can become a job template later. Classify uses the interface descriptions together with the config to decide which ports migrate, and runs both from the laptop across all sites and as a job for one site.

## Slide 3: Every job starts by locking down its targets
1
Parse
odyssey_parse_devices
Survey string to a hostname list
reused
2
Validate
input_validation + ibns_input_validation
Hostname format, change number, max switches per job
reused + new
3
Match
inventory_lookup
Exactly one inventory match per hostname; empty list refused
edited
4
One site
ibns_target.yml
Refuses targets spread over more than one site
new
5
Run id
ibns_target.yml
One id per job; names every snapshot and backup
new
ansible-playbook ansible/playbooks/ibns_precheck.yml -e device_hostnames=SW1,SW2
# every playbook begins with:
- ansible.builtin.import_playbook: ibns_target.yml
Notes: These guardrails come from the SWIM repo and are already proven in production. I added two: one site per job, and a single run id so a job's snapshots and backups can be found later. Matched switches land in the ibns_targets group, which every later play targets.

## Slide 4: Every read and every change goes through Catalyst Center
Ansible job
AAP execution environment, runs locally
Renders the CLI from repo templates and filters
No SSH, no switch login
catc_device
Inventory
Find switch, version, reachability; resync after a change
catc_cli_read
Command Runner
show running-config, sessions, AAA, flash (read-only)
catc_cli_push
Template Programmer
Every change: backup copy, convert, golden, re-point, rollback, cleanup, write memory
One template per switch: IBNS2_<hostname>
Each push replaces the template content, commits a new version (comment: run id, stage, step) and deploys it. The version history in Catalyst Center is the change record for that switch; the same CLI and its result are also saved with the run's snapshots.
Notes: This follows the team rule that config goes through DNAC. Reads use Command Runner, which only accepts read-only commands, so the config mode is worked out from the running config. Changes are rendered by Ansible and pushed as template content; exec commands like the conversion use the template's MODE_ENABLE and INTERACTIVE syntax to answer the prompt. The three modules are small Python files on ansible-core only, so the existing execution environment works without new collections. One thing to prove in the lab: whether an API deployment also writes memory, as the UI does by default.

## Slide 5: Every change stage follows the same five steps
1
Pre-check
Version, ClearPass UP, config mode, flash, held ports. Fails = switch skipped
2
Backup
Running config to the snapshot store and to switch flash
3
Change
Convert, or golden + re-point, or cleanup. Dry run stops here
4
Post-check
Config checks, RADIUS UP, per-endpoint session compare
5
Save or act
Pass: write memory. Fail: stage-specific action, never a blind save
Stage | On pass | On fail
1 Convert | write memory | Not saved; FIX-FORWARD-REQUIRED (no reload)
2 Golden | write memory | Automatic re-point back to converted, re-check
3 Cleanup | write memory | Not saved; restore objects from backup
Notes: One pattern, three stages, so reviewers learn it once. The important rule is the last step: we only write memory after the post-check passes. Each stage has its own failure action, because the one-way conversion can't be undone the way the golden config can.

## Slide 6: Stage 1 converts in place; stage 2 moves ports onto golden
Stage 1: convert
ibns_stage1_convert.yml · one-way
Runs authentication convert-to new-style
Converted config behaves like the legacy config
write memory only after the post-check passes
Failure: fix forward in new-style; console restore last
#MODE_ENABLE + #INTERACTIVE
authentication convert-to new-style
<IQ>continue<R>yes
Stage 2: golden
ibns_stage2_golden.yml · reversible per port
Golden global config added alongside the converted one
One golden template per port class
Each access port re-pointed in one push
Failure: automatic re-point back, then re-check
interface Gi1/0/5
source template IBNS2_MAB
no service-policy type control ...
no access-session ...
The RADIUS server group is read from each switch's own config, so one golden template set works across every site.
Notes: Stage 1 can't be reversed with a command, so it carries no automated rollback; it's made safe instead by proving in the lab that conversion keeps behaviour identical. Stage 2 is where behaviour changes, and it's fully reversible per port. The RADIUS group name is read from each switch, so the golden config works across sites.

## Slide 7: A port is never without authentication, even mid-change
Converted
after stage 1
access-session port-control auto
mab
dot1x pae authenticator
service-policy type control
subscriber POLICY_Gi1/0/5
Template attached
first command
source template IBNS2_MAB
+ converted lines still there
(interface lines win)
Golden
lines stripped
source template IBNS2_MAB
(template now applies)
Rollback runs the same steps in reverse
Restore the saved converted lines first, then remove the template. The data comes from the stage 2 snapshot, so the rollback job also works days later.
Both command lists come from ibns_repoint_commands and ibns_rollback_commands in the filter plugin; unit tests check the order.
Notes: This ordering is the reason for the convert-first approach. Interface-level commands override the template, so we attach the template while the converted lines still protect the port, then strip them. ibns_repoint_commands and ibns_rollback_commands in the filter plugin generate exactly these command lists, and unit tests check the ordering.

## Slide 8: What the post-check compares, and when
1
Config checks
every post-check
Golden template on every planned port
No auth config on trunks or uplinks
Port class unchanged
RADIUS servers to ClearPass UP
2
Live sessions
in the window
Matched per MAC address
Same port, still authorized
Same domain and method
Same VLAN and ACL; no fail-open
3
Next-day check
next morning
Against the daytime baseline
Ports authorized then, not now
Read-only; separate job
Issues: fix per port or roll back
All comparison logic lives in one filter plugin (ibns_filters.py) with unit tests, so it can be reviewed and tested off the network.
Notes: New endpoints never fail a check; only regressions do. The failure threshold is a variable, default zero. The next-day check exists because change windows are after hours and most users have gone home, so layer 2 only sees what's plugged in.

## Slide 9: Each port migrates only when description and config agree
Description
says what the port is for
PRN-2F-HR
role: printer
Config
says what the port does
mab
(no dot1x pae)
class: mab-only
Agree?
role allows this class (ibns_port_roles)
Migrate
Auth port, they agree: gets the golden template for its class
Hold
Auth port, they disagree or no rule matches: stays converted, listed in pre-check
Leave
Trunk, uplink, static: never touched
Port | Description | Role | Config class | Action
Gi1/0/1 | USER-PC-2F-014 | user | multi-domain | migrate → IBNS2_MDA
Gi1/0/2 | PRN-2F-HR | printer | mab-only | migrate → IBNS2_MAB
Gi1/0/3 | AP-3F-01 | ap | dot1x+mab | hold: AP with dot1x?
Gi1/1/1 | UPLINK TO DIST-SW1 | uplink | trunk | leave
The template always comes from the config class, so migrating never changes how a port authenticates. Rules live in group_vars; the laptop script and the jobs share them.
Notes: Every interface has a description, so we use it as a second opinion. The description gives a role through an ordered list of regex rules; the config gives a class. A port migrates only when the role allows that class. Anything that disagrees, or has no matching rule, is held: it keeps the converted config, still authenticating, and the pre-check lists it. The laptop script runs the same code over every discovered switch and lists the unmatched description patterns, which is how we build the rules from real data instead of guessing.

## Slide 10: Snapshots connect jobs that run on different days
Snapshot store
per switch, named by run id
laptop: local folder · AAP: Artifactory
Baseline job
writes baseline-latest.json
Every stage
writes running-before-<stage>.cfg
Stage 2
writes stage2-rollback-latest.json
Next-day / rollback
read baseline and rollback data
Every job also publishes its result (set_stats) as an AAP artifact; the existing NetValidator webhook forwards it to Odyssey.
Notes: AAP runs each job in a fresh container, so anything a later job needs has to live outside it. Laptop runs use a local folder; in AAP the plan is a generic Artifactory repo. How the job gets Artifactory credentials is an open question for the platform team.

## Slide 11: Most of ud00 is reused; the IBNS logic is new
13
Copy unchanged
Helios workflow, deploy.sh
Helm helper .tpl files
Projects, notifications
dnac.py and dnac.yml
Parse and validation roles
12
Copy and edit
ansible.cfg, requirements
Credentials, input sources
Execution environment
Inventories and source
inventory_lookup (run locally)
3
Replace
README
Job templates
Survey specs
38
New
Filters, DNAC modules, 28 tests
13 roles, 9 playbooks
Golden templates
Discovery, classify scripts
Runbook
Not carried over: SWIM, SD-WAN and CML roles and playbooks, vManage plugin, ud00's switch login file.
Notes: Reusing the platform pieces means reviewers already know the pipeline, the AAP layout and the guardrails. The new work is concentrated in the filter plugin, the roles and the templates. The README in the repo has the full file-by-file map.

## Slide 12: Push to Git; Helios builds the AAP job templates
Laptop
test, push
GitHub
dev branch
Helios
render aap_payload
DEV AAP
lab runs
PROD AAP
release branch
Job templates Helios creates in AAP
ibns_classify
ibns_baseline
ibns_precheck
ibns_stage1_convert
ibns_stage2_golden
ibns_nextday_check
ibns_rollback_golden
ibns_stage3_cleanup
noop
Surveys
Read-only jobs ask only for hostnames (comma separated, one site)
Change jobs add the ServiceNow change number and Dry Run (default true)
Jobs carry the DNAC service ID from RBC Vault; no switch login, nothing secret in the repo
Notes: Same pipeline as ud00, untouched. Pushing to dev creates or updates the job templates in DEV AAP; the release branch promotes to PROD. The pipeline never launches a job; an operator launches each one from AAP with the survey.

## Slide 13: Safety rails are on by default
✓
Dry run
Default true on every change job
✓
Change number
Required when dry run is false
✓
Exact match
One inventory match per hostname
✓
One site
Targets across sites are refused
✓
Job size
Max 20 switches per job, 5 at a time
✓
Save on pass
write memory only after post-check
✓
Protected names
Cleanup never removes golden objects
✓
DNAC only
No SSH to switches; logins from Vault
Notes: All of these are settings in group_vars/all.yml or survey defaults, so the team can tighten or relax them in review. The limits (20 per job, 5 at a time) are my starting proposal.

## Slide 14: Built and proven in six steps, lab first
1
Foundation
Filters, DNAC client, tests
Gate: pytest: 28 pass
2
Read-only
Classify, pre-check, baseline
Gate: Runs on lab switch
3
Stage 1
Convert
Gate: Lab conversion verified
4
Stage 2
Golden + rollback
Gate: Forced rollback works
5
Close-out
Next-day, cleanup
Gate: Clean next-day run
6
AAP
Job templates, surveys
Gate: Runs in DEV AAP
Notes: Each step ends with something that runs, so mistakes surface early. Nothing reaches AAP until the playbooks have worked from my laptop against the lab switch, including a deliberately broken golden template to prove the automatic rollback.

## Slide 15: To confirm before the first lab run
1
DNAC account
Can the DNAC service ID run Command Runner and deploy templates?
2
Snapshot store
Artifactory generic repo and how jobs get its credentials
3
Deploy behaviour
Does an API template deployment also write memory?
4
App code
New app code for IBNS, or live under ud00?
5
Golden standard
Approved IBNS 2.0 config, closed or low-impact mode
6
Descriptions + lab
Port description standard for the classify rules; parsers and timers on real output
Notes: The execution environment question is gone: the DNAC modules need ansible-core only. The first three are platform questions for Gurkirat. The rest decide the content of the golden templates and the timing values, and get settled in the lab.

## Slide 16: Next steps
Questions and feedback welcome
1
Create the repo and copy the ud00 pieces
2
Type the filter plugin and pass the tests
3
Classify all sites; run pre-check and baseline in the lab
4
Prove stage 1, stage 2 and the rollback in the lab
5
Push to dev and run the jobs in DEV AAP
Notes: I'll start with the repo and the read-only jobs this week, in parallel with the platform questions, since onboarding has lead time.